TSIU03
PROJECT PLAN

Project group: 41	Date: 2015-09-24

1) Group Members

Group Member	E-mail	Responsibilities in the Project
Matteus Laurent ML	Matla782	Project manager
Oscar Petersson OP	Oscpe262	Document manager
Johan Levinsson JL	Johle727	Debug chief
Erik Peyronson EP	Eripe320	VGA and Keyboard chief
Philip Johansson PJ	Phijo078	Design chief
Niklas Blomqvist NB	Nikbl635	Sound chief

2) Customer

Petter Källström

3) Project Resources

DE2 board, Class-d amplifier, ps/2 keyboard, vga-screen, sound source, computer, 6 happy retards

4) Documents to Submit and Deadlines

Document	Deadline
Requirement Specification	2015-09-25
Time Report 1	2015-09-25
Time Report 2, 3, ...	Every Friday
Project Plan	2015-10-11
Design Specification	2015-10-11
First presentation	2015-10-13
Project Report	2015-11-09
Final presentation	2015-11-11

5) Project Tasks

Task	Allocated time (hours)	Group Member in Charge	Project Week*
1.Project plan	12	ML, all	1-2
2.Design overview	18	PJ, all	1-2
3.Detailed overview	14	PJ, all	2
4.a Design specification draft	20	OP, all	2
4.b Design specification final	12	OP, all	3
5.First presentation	12	ML, all	3
6.Test Bench code	30	JL, EP, OP	3-4
7.Vga code	18	EP, OP, JL	3-4
8.Keyboard code	6	EP, OP JL	3-4
9.Snd-driver code	0	NB	3-4
10.Vol/bal code	18	NB, ML, PJ	3-4
11.Sound analysis	18	NB, ML, PJ	3-4
12.First prototype	3	ML, ML, PJ	4
13.Debugging	120	JL, all	4-5
14.Time plan	0.1*6	OP, all	1,2,3,4,5,6
15.Report first hand in	48	OP, all	5
16.Report final hand in	24	OP, all	6
17.Final presentation	18	ML, all	6
19.
20.
...
TOTAL TIME:	391.0

*The duration of the project is 6 weeks, from the first meeting with the supervisor to the final presentation. Write in which week (from 1 to 6) you plan to do each task.

(You can add/remove as many rows in the table as you need. Most projects usually include around 20 tasks.)
(The Project Plan should be 2-3 pages.)