TSIU03
TIME REPORT

Project group: 41	Report number: 7	Date: 2015-11-09

1) Hours spent on the project and tasks.

Group Member	Worked hours / this week	Worked hours / so far	Tasks done this week
Matteus	4,5	77,0
Oscar	12	67,0
Erik		70,5
Johan		53,5
Philip		68,5
Niklas		65,5
Alla

2) Status of the project.

Finished tasks
Project plan, Design spec (draft), first presentation (slides), Design spec (final rev.), first pres. Preparation, Presentation, modules done for merging, testbenches, system merge

Ongoing tasks
Debugging Prio 2 issues, report writing

Planned tasks
final presentation preparations

Difficulties found this week and if/how you have faced them